## DMAIC
Six Sigma Templates

## Breakthrough Strategy
Step | MAIC | Focus | Action | Question | Know | See | Tool | Data | Location
1 | Measure | CTQ | Select CTQ Characteristic | Does the selected CTQ offer high impact -- quality, cost or time ? | Selection criteria and timeframe | Decision Matrix | Brainstorming, pareto, C&E analysis, process/design FMEA, COPQ, RTY, dpu, Y.norm | Continuous and discrete data, Spec Limits for short term, | Simulator, QA/QC, Manufacturing
2 | Measure | CTQ | Define Performance Standards | Can stated performance standards satisfy customer and business needs? | Mean, target, Spec Limits, functional limits, required capability | Graphical presentation of requirements | Communication with customers, Strat Plan, Design specifications | Reliability and warranty data, engineering data, Mean, Standard Deviation, Spec Limits for short term | Simulator
3 | Measure | CTQ | Validate Measurement System | Is the current measurement system acceptable by conventional standards? | P/T and R&R values | GRR Table | Gage R&R spreadsheet | Sample Data over process range | Lab/Floor
4 | Analyze | CTQ | Establish Product Capability | Does the existing capability of this CTQ need to be improved to meet performance requirements? | Baseline m, s, Cp, Cpk, Pp, Ppk | Minitab Capability Six Pack and Six Sigma Macro Reports | Minitab | n= 500 subgroups = 100 subgroup size = 5, record Y and X's for future use | Simulator
5 | Analyze | CTQ | Define Performance Objectives | Do we know the extent to which the variation must be reduced to meet objectives? | Baseline and target m, s, Cp, Cpk, Pp, Ppk | Picture of "is" and "ought" | Minitab | From capability analysis and performance standards | Previous outputs
6 | Analyze | CTQ | Identify Variation Sources | Do we know the major family of variation? | Inputs, noise variables | Process Map and capabilities of each input variables | Process Map, FMEA, Cause and Effect Matrix, Multivari chart | Process understanding | Grey Matter
7 | Improve | CTQ and CTP (Critical to Process) | Screen Potential Causes | Are the leverage CTP's known? | Direction of effect and sensitivity of selected CTP's with respect to m, s | Graphical and tabular form | Main Effects Plot, ANOVA, e (SSe/SSt), Autocorrelation, Regression | Data from product capability study
8 | Improve | CTQ and CTP (Critical to Process) | Study Key Relationships | Do we know what relationships among the CTP's must be controlled ? | Main effects, Interactions, clear of confounding | Graphical and tabular form | Main Effects Plot,Interaction Plots, ANOVA, e (SSe/SSt), Autocorrelation, Regression
9 | Improve | CTP | Establish Operating Tolerances | Do we know the functional limits for the CTP's? | Regression coefficients and coding information | Equation and graphical | Main effects plots, regression, interactions plot
10 | Control | CTP | Validate Measurement System (for X's) | Is the current measurement systems acceptable by conventional standards for the CTP's? | P/T and R&R values | GRR Table | Gage R&R spreadsheet | Sample Data over process range | Shop floor
11 | Control | CTP | Determine Process Capability (Y and X's) | Can process operate within chosen limits to a 6s capability? | Baseline m, s, Cp, Cpk, Pp, Ppk | Minitab Capability Six Pack and Six Sigma Macro Reports | Minitab | Rational subgroups of continuous data | Shop floor
12 | Control | CTP | Implement Process Control System | Can objectives be consistently met? | Control charts, CTQ yield information | Six Sigma Reports | Six Sigma Macro, control chart option

## SS Project Plan
Six Sigma Project Template
Project Name
Group Name |  |  | Black Belt Name
Department Name |  |  | Team Members
Project Champion Name
Process Owner Name
Total FTE's Performing Process
Total Cost of Process (000's)
Problem Statement | Defect FTE's (if app.) |  | Cost of Defect
Provide complete and detailed description | State the Problem/Defect
State the Defect or Undesired Event
Exclude solutions
Do not include causes
Review with Finance
Define measurement source
Include Baseline data (if available)
IncludeTimeframe
Include conditions surrounding problem
Project Objective/Desired State | State the Project Objective/Desired State and make sure it links back to the Problem Statement
Clearly define and quantify | State the Project Objective
70% Defect Reduction Sought
Include Entitlements - Best Performance
Include available benchmark data
Benefits ($000's) | Cost Benefits |  | Client/Employee Benefits
Include Shareholder/Cost Benefits | FTE Cost Savings |  |  | Internal/External Client Benefits
Include Client Service Benefits - Intrnl/Ext | Other Cost Savings |  |  | Employee Benefits
Cost Benefits outside of Group
Employee Benefits | Revenue
| Total Cost Benefits | 0
Dependencies
Significant Systems Development | Description:
Major Capital Investment
External Considerations
Potential to Leverage
Description:
Other Information | Include any other information related to the Project as necessary

## Project Action Plan
Project Action Plan
Project |  |  | Black Belt
Process Owner |  |  | Date
What | How | Who | When |  | Deliverables
(Action to Take) | (Action Steps) | (Accountable) | Start | Finish

## CTQ Template
Critical to Quality Characteristics
Project Name:
Project Description:
Project Managers:
Date:
How to Satisfy Wants
What the customer wants
Total

## SIPOC
SIPOC
Who are the suppliers for our product or service? | What do the suppliers provide to my process? | What are the start and end points of the process associated with the problem and the major steps in the process. | What product or service does the process deliver to the customer? | Who are the customers for our product or service? What are their requirements for performance
Suppliers | Input | Process (High Level) | Output | Customers
1 | 1 | Start Point: | 1 | 1
| 2 |  |  | 2
| 3 |  | 2 | 1
2 | 1 |  |  | 2
| 2 | Operation or Activity | 3 | 1
| 3 | 1 |  | 2
3 | 1 | 2 | 4 | 1
| 2 | 3 |  | 2
| 3 | 4 | 5 | 1
4 | 1 | 5 |  | 2
| 2 | 6 | 6 | 1
| 3 | 7 |  | 2
8
9
10
11
End Point:

## SIPOC (blank)
Suppliers | Inputs | Process | Outputs | Customers
(Providers of the required resources) | (Resources required by the process) | (Top level description of the activity) | (Deliverables from the process) | (Anyone who receives a deliverable from the process)
|  | Requirements |  | Requirements

## Process Analysis
Process Analysis Worksheet
Process Name (& boundaries):
Process Owner(s):
Step No. | Activity | Responsible | Volume | No. | Total hrs | NVA | NVA hrs/
|  | position | per week | individuals | per week | (Y/N?) | week
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8)
Sum=

## Fishbone
Effect
(Y)
Management
Man
Method
Measurement
Machine
Material
Cause
Cause
Cause
Cause
Cause
Cause
Cause
Cause
Cause
Cause
Cause

## Brainstorm
Brainstorm Potential Root Causes
Problem Statement:
Rank | Potential Root Cause | Supporting Data & Analysis?* | Source? | Who? | When?
*Common types of data and analysis |  | Analysis description:
Detailed Process Review |  | Careful walkthrough of the process step by step to determine the source, nature and frequency of the problem
Process Mapping |  | Detailed process flow analysis to understand all the steps of the process, how the problem occurs and to document the process flow
Visual Analysis |  | Visual examination of the problem and visual documentation such as digital photos and videos
Cause and Effect (Event) Analysis |  | Examination of the potential relationship of factors and or event conditions on the problem
Data Collection and Analysis |  | Measurement of performance from the product or process and an analysis of current data and associated factor effects
Additional Tests and Experiments |  | Additional tests or experiments designed to understand the current situation and determine the root cause

## FDM
Function Deployment Matrix
Outputs/ Outcomes
|  | Output 1 | Output 2 | Output 3 | Output 4 | Output 5 | Output 6 | Output 7 | Output 8 | Output 9 | Score
Inputs Wght | Wght | 1 | 2
Input 1 |  | 10 | 2 | [7 empty] | 14
Input 2
Input 3
Input 4
Input 5
Input 6
Input 7
Input 8
Input 9
Input 10
Input 11
Input 12
Score |  | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Risk Assessment
Risk Assessment Form
List the Solution or | Failure Mode | Severity | Probability | Score | Action | Owner | Due
Major Elements of | (What can go wrong) | (1-10) | (10 is | (High scores | Plan |  | Date
Your Solution | List each failure mode | 10 is Worst | very probable) | need attention)
1.Solution
a)
b)
c)
2. Solution | a)
b)
c)
3. Solution | a)
b)

## Solution Evaluation Form
Solution Evaluation Form
List Root Cause(s) | List Solutions | % Effect | Estimated Cost | Complexity | Estimated Benefit | Risk* | Priority | Validation?
Root Cause 1 | Solutions 1
|  | % of | cost | time or | savings | High | Order | Need
|  | effect | of | effort to | due to | Medium | of potential | to
|  | solution | solution | implement | solution | or | solution | verify
|  | will have | implementation | short term? | or | Low | implementation | effectiveness
|  | on the |  | long term? | improvement |  | 1st, 2nd, 3rd | of solution
|  | root cause |  |  | in customer
satisfaction
Root Cause 2
* Use Risk Assessment Form

## Data Collection Plan
Data Collection Plan
Define What to Measure |  |  | Define How to Measure |  |  | Who will | Sample Plan
Do it?
| Type of | Operational | Measurement | Data Tags Needed | Data Collection | Person(s) | What? | Where? | When? | How Many?
Measure | Measure | Definition | or Test Method | to Stratify the Data | Method | Assigned
Name of | X or Y | Clear definition of | Visual | Data tags are | Manual? | State | What | Location | How | The number
parameter | attribute or | the measurement | inspection | defined for the | Spreadsheet? | who has | measure is | for | often | of data
or condition | discrete | defined in such a | or automated | measure. Such | Computer based? | the | being | data | the | points
to be | data, | way as to achieve | test? | as: time, date, | etc. | responsibility? | collected | collection | data | collected
measured | product or | repeatable results | Test instruments | location, tester, |  |  |  |  | is | per sample
| process | from multiple | are defined. | line, customer, |  |  |  |  | collected
| data | observers |  | buyer, operator,
|  |  | Procedures for | etc.
data collection
are defined.

## Xs and Ys
Measure Relationships
Responses or Outputs (Ys) |  |  |  | Factors (Xs)
Dependent Variable | USL | LSL | Target | Independent Variable(s) | USL | LSL | Target

## Timeline
Root Cause Analysis Timeline
Project Name: |  |  |  |  | Start Date: |  | 2002-06-10
Use lines and or color bars to indicate start and stop dates for each activity
Phase: | Activity | Start Date | End Date | Assigned to: | 2002-06-10 | 2002-06-11 | 2002-06-12 | 2002-06-13 | 2002-06-14 | 2002-06-15 | 2002-06-16 | 2002-06-17 | 2002-06-18 | 2002-06-19 | 2002-06-20 | 2002-06-21 | 2002-06-22 | 2002-06-23 | 2002-06-24 | 2002-06-25 | 2002-06-26 | 2002-06-27 | 2002-06-28 | 2002-06-29 | 2002-06-30 | 2002-07-01 | 2002-07-02 | 2002-07-03 | 2002-07-04 | 2002-07-05 | 2002-07-06 | 2002-07-07 | 2002-07-08 | 2002-07-09 | 2002-07-10
1. Define and
Contain the
Problem
2. Measure the
Problem
3. Perform
Root Cause
Analysis
4. Plan and
Implement
Improvement
5. Assess
Effectiveness of
Improvement
6. Standardize
and Control
7. Realize and
Reflect

## DOE 2^2 template
22 Factorial Design (with up to 5 replicates)
|  |  |  | Replications |  |  | ----- | ----
| A | B | AB | 1 | 2 | 3 | 4 | 5 | Sum | Average
| -1 | -1 | 1 | 28 | 25 | 27 |  |  | 80 | 26.6667
| 1 | -1 | -1 | 36 | 32 | 32 |  |  | 100 | 33.3333
| -1 | 1 | -1 | 18 | 19 | 23 |  |  | 60 | 20
| 1 | 1 | 1 | 31 | 30 | 29 |  |  | 90 | 30
ave - | 23.3333 | 30 | 26.6667
ave + | 31.6667 | 25 | 28.3333
effect | 8.3333 | -5 | 1.6667
[12 empty] | B - | B +
[11 empty] | A - | 26.6667 | 20
[11 empty] | A + | 33.3333 | 30
ANOVA
Sources | SS | df | MS | F | F table | Stat sig ? | a
A | 208.3333 | 1 | 208.3333 | 53.1915 | 11.2586 | * | 0.01
B | 75 | 1 | 75 | 19.1489 | 11.2586 | *
AB | 8.3333 | 1 | 8.3333 | 2.1277 | 11.2586 | ns
Error | 31.3333 | 8 | 3.9167
Total | 323 | 11
REGRESSION MODEL
Intercept |  | 27.5
A coefficient |  | 4.1667
B coefficient |  | -2.5
AB coefficient |  | 0
PREDICTION EQUATION
A | 1
B | 1
Y-hat | 29.1667
RESIDUALS
|  |  | Actual | Pred | Residual | rank | Perc | Z
1 | -1 | -1 | 28 | 25.8333 | 2.1667 | 1 | 2.5 | -1.96
2 | -1 | -1 | 25 | 25.8333 | -0.83333 | 16 | 77.5 | 0.75542
3 | -1 | -1 | 27 | 25.8333 | 1.1667 | 5 | 22.5 | -0.75542
4 | -1 | -1 | 0 | 0 | 0 | 7 | 32.5 | -0.45376
5 | -1 | -1 | 0 | 0 | 0 | 7 | 32.5 | -0.45376
1 | 1 | -1 | 36 | 34.1667 | 1.8333 | 3 | 12.5 | -1.1503
2 | 1 | -1 | 32 | 34.1667 | -2.1667 | 18 | 87.5 | 1.1503
3 | 1 | -1 | 32 | 34.1667 | -2.1667 | 18 | 87.5 | 1.1503
4 | 1 | -1 | 0 | 0 | 0 | 7 | 32.5 | -0.45376
5 | 1 | -1 | 0 | 0 | 0 | 7 | 32.5 | -0.45376
1 | -1 | 1 | 18 | 20.8333 | -2.8333 | 20 | 97.5 | 1.96
2 | -1 | 1 | 19 | 20.8333 | -1.8333 | 17 | 82.5 | 0.93459
3 | -1 | 1 | 23 | 20.8333 | 2.1667 | 1 | 2.5 | -1.96
4 | -1 | 1 | 0 | 0 | 0 | 7 | 32.5 | -0.45376
5 | -1 | 1 | 0 | 0 | 0 | 7 | 32.5 | -0.45376
1 | 1 | 1 | 31 | 29.1667 | 1.8333 | 3 | 12.5 | -1.1503
2 | 1 | 1 | 30 | 29.1667 | 0.83333 | 6 | 27.5 | -0.59776
3 | 1 | 1 | 29 | 29.1667 | -0.16667 | 15 | 72.5 | 0.59776
4 | 1 | 1 | 0 | 0 | 0 | 7 | 32.5 | -0.45376
5 | 1 | 1 | 0 | 0 | 0 | 7 | 32.5 | -0.45376
EFFECTS PLOT
score | rank | (R-0.5)/n | z score
8.3333 | 3 | 0.83333 | 0.96742
-5 | 1 | 0.16667 | -0.96742
1.6667 | 2 | 0.5 | 0

## DOE 2^3 template
23 Factorial Design (with up to 5 replicates) | [14 empty] | ANOVA
[8 empty] | Replications |  |  | ----- | ----
| A | B | C | AB | AC | BC | ABC | 1 | 2 | 3 | 4 | 5 | Sum | Average
(1) | -1 | -1 | -1 | 1 | 1 | 1 | -1 | 1 | 2 | 3 |  |  | 6 | 2
a | 1 | -1 | -1 | -1 | -1 | 1 | 1 | 1 | 2 | 3 |  |  | 6 | 2
b | -1 | 1 | -1 | -1 | 1 | -1 | 1 | 1 | 2 | 3 |  |  | 6 | 2
ab | 1 | 1 | -1 | 1 | -1 | -1 | -1 | 1 | 2 | 3 |  |  | 6 | 2
c | -1 | -1 | 1 | 1 | -1 | -1 | 1 | 1 | 2 | 3 |  |  | 6 | 2
ac | 1 | -1 | 1 | -1 | 1 | -1 | -1 | 1 | 2 | 3 |  |  | 6 | 2
bc | -1 | 1 | 1 | -1 | -1 | 1 | -1 | 1 | 2 | 3 |  |  | 6 | 2
abc | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 |  |  | 6 | 2
ave - | 2 | 2 | 2 | 2 | 2 | 2 | 2
ave + | 2 | 2 | 2 | 2 | 2 | 2 | 2
effect | 0 | 0 | 0 | 0 | 0 | 0 | 0
[17 empty] | B - | B +
[16 empty] | A - | 2 | 2
[16 empty] | A + | 2 | 2
[17 empty] | C- | C+
[16 empty] | A - | 2 | 2
[16 empty] | A + | 2 | 2
[17 empty] | C- | C+
[16 empty] | B - | 2 | 2
[16 empty] | B + | 2 | 2
Sources | SS | df | MS | F | F table | Stat sig ? | a
A | 0 | 1 | 0 | 0 | 8.531 | ns | 0.01
B | 0 | 1 | 0 | 0 | 8.531 | ns
C | 0 | 1 | 0 | 0 | 8.531 | ns
AB | 0 | 1 | 0 | 0 | 8.531 | ns
AC | 0 | 1 | 0 | 0 | 8.531 | ns
BC | 0 | 1 | 0 | 0 | 8.531 | ns
ABC | 0 | 1 | 0 | 0 | 8.531 | ns
Error | 16 | 16 | 1
Total | 16 | 23
REGRESSION MODEL
Intercept |  | 2
A coefficient |  | 0
B coefficient |  | 0
C coefficient |  | 0
AB coefficient |  | 0
AC coefficient |  | 0
BC coefficient |  | 0
ABC coefficient |  | 0
PREDICTION EQUATION
A | 1
B | 1
C | 1
Y-hat | 2

## PPM
Parts per Million Calculator
This is a simple sigma level calculator
Enter process sigma level, compute PPM
Process Sigma Level -> | 6
PPM | 3.3977
Percent | 0.0003398%
Enter percent, compute PPM and process sigma level
If the percent is less than 1, you must use the percent sign after the number (e.g., 0.01%)
Percent -> | 0.00034%
PPM | 3.4
Process Sigma Level | 5.9999
Enter DPMO, compute process sigma level
DPMO -> | 3.4
Process Sigma Level | 5.9999

## no shift
Sigma Level (no shift) Calculator
NO 1.5 SIGMA SHIFT IN THESE CALCULATIONS
Enter process sigma level, compute PPM
Process Sigma Level -> | 6
PPM | 0.00098659
Percent | 9.866e-08%
Enter percent, compute PPM and process sigma level
Percent -> | 1%
PPM | 10000
Process Sigma Level -> | 2.3263
Enter DPMO, compute process sigma level
Process Sigma Level -> | 4.4999
DPMO | 3.4

## RTY
Rolled Throughput Yield Calculator
Step | DPMO | DPMO/1,000,000 | 1-(DPMO/1,000,000)
1 | 5000 | 0.005 | 0.995
2 | 15000 | 0.015 | 0.985
3 | 1000 | 0.001 | 0.999
4 | 50 | 5e-05 | 0.99995
RTY= | 0.99472

## DPMO Calculator
DPMO Calculator
This template calculates the DPMO using the number of defects.
Total number of units: | 2500
Number of defects: | 4
Opportunities for Error in one unit: | 20
DPMO = | 80
Not sure of what goes into the units?
The Data Processing Dept supervisor wants to calculate the DPMO of data entry errors in her dept.
A total of 2,500 forms were processed that day, and the supervisor finds 4 fields with error.
There are 20 entry fields on each data entry form.
For this scenario:
Total number of units = 2,500
Number of defects = 4
Opportunities for error in one unit = 20

## DPMO>Sig>Cpk
Conversion Calculator
Sigma Conversion Table
Defects Per Million Opportunities | Sigma Level (With 1.5 Sigma Shift)* | Cpk (Sigma Level / 3) With 1.5 Sigma Shift*
933200 | 0 | 0
915450 | 0.125 | 0.042
894400 | 0.25 | 0.083
869700 | 0.375 | 0.125
841300 | 0.5 | 0.167
809200 | 0.625 | 0.208
773400 | 0.75 | 0.25
734050 | 0.875 | 0.292
691500 | 1 | 0.333
645650 | 1.125 | 0.375
598700 | 1.25 | 0.417
549750 | 1.375 | 0.458
500000 | 1.5 | 0.5
450250 | 1.625 | 0.542
401300 | 1.75 | 0.583
354350 | 1.875 | 0.625
308500 | 2 | 0.667
265950 | 2.125 | 0.708
226600 | 2.25 | 0.75
190800 | 2.375 | 0.792
158700 | 2.5 | 0.833
130300 | 2.625 | 0.875
105600 | 2.75 | 0.917
84550 | 2.875 | 0.958
66800 | 3 | 1
52100 | 3.125 | 1.042
40100 | 3.25 | 1.083
30400 | 3.375 | 1.125
22700 | 3.5 | 1.167
16800 | 3.625 | 1.208
12200 | 3.75 | 1.25
8800 | 3.875 | 1.292
6200 | 4 | 1.333
4350 | 4.125 | 1.375
3000 | 4.25 | 1.417
2050 | 4.375 | 1.458
1300 | 4.5 | 1.5
900 | 4.625 | 1.542
600 | 4.75 | 1.583
400 | 4.875 | 1.625
230 | 5 | 1.667
180 | 5.125 | 1.708
130 | 5.25 | 1.75
80 | 5.375 | 1.792
30 | 5.5 | 1.833
23.4 | 5.625 | 1.875
16.7 | 5.75 | 1.917
10.1 | 5.875 | 1.958
3.4 | 6 | 2
The table assumes a 1.5 sigma shift because
processes tend to exhibit instability of that magnitude
over time. In other words, although statistical tables
indicate that 3.4 defects / million is achieved when
4.5 process standard deviations (Sigma) are between
the mean and the closest specification limit, the
target is raised to 6.0 standard deviations to
accommodate adverse process shifts over time and
still produce only 3.4 defects per million opportunities.

## Six Sigma Project
Six Sigma Project Timeline
Project Name:
ID | Task | Hours | Start | End | Status | Comments
1 | Define | 1 Wk | 2001-09-25 08:00 | 2001-10-01 17:00 | Complete
2 | Measure | 17 Wks | 2001-10-02 08:00 | 2002-01-25 11:34 | Working
4 | Project Direction Meeting | 0.96667 | 2002-01-22 08:00 | 2002-01-22 08:58
5 | Assign Roles | 5 | 2002-01-22 08:00 | 2002-01-22 08:05
6 | Review Status | 10 | 2002-01-22 08:05 | 2002-01-22 08:15
7 | Review Schedule | 5 | 2002-01-22 08:15 | 2002-01-22 08:20
8 | Project Direction Decision | 33 | 2002-01-22 08:20 | 2002-01-22 08:53
9 | Clarify Options | 10 | 2002-01-22 08:20 | 2002-01-22 08:30
10 | ID Decision Maker | 2 | 2002-01-22 08:30 | 2002-01-22 08:32
11 | Vote on Options | 2 | 2002-01-22 08:32 | 2002-01-22 08:34
12 | Dialog A | 5 | 2002-01-22 08:34 | 2002-01-22 08:39
13 | Vote on Options | 2 | 2002-01-22 08:39 | 2002-01-22 08:41
14 | Dialog B | 5 | 2002-01-22 08:41 | 2002-01-22 08:46
15 | Vote on Options | 2 | 2002-01-22 08:46 | 2002-01-22 08:48
16 | Decision Maker Decides | 5 | 2002-01-22 08:48 | 2002-01-22 08:53
17 | Assign Tasks | 5 | 2002-01-22 08:53 | 2002-01-22 08:58
18 | Work Tasks | 2 Days | 2002-01-22 08:58 | 2002-01-24 08:58
19 | Process Map & Data Meeting | 96 | 2002-01-24 08:58 | 2002-01-24 10:34
20 | Review Status | 10 | 2002-01-24 08:58 | 2002-01-24 09:08
21 | Report Weekly Deliverable | 10 | 2002-01-24 09:08 | 2002-01-24 09:18
22 | Review Schedule | 5 | 2002-01-24 09:18 | 2002-01-24 09:23
23 | Process Map | 42 | 2002-01-24 09:23 | 2002-01-24 10:05
24 | Goal | 2 | 2002-01-24 09:23 | 2002-01-24 09:25
25 | Process | 5 | 2002-01-24 09:25 | 2002-01-24 09:30
26 | Exercise | 0.5 | 2002-01-24 09:30 | 2002-01-24 10:00
27 | Review | 5 | 2002-01-24 10:00 | 2002-01-24 10:05
28 | Key Data Decision | 24 | 2002-01-24 10:05 | 2002-01-24 10:29
29 | Clarify Options | 5 | 2002-01-24 10:05 | 2002-01-24 10:10
30 | ID Decision Maker | 1 | 2002-01-24 10:10 | 2002-01-24 10:11
31 | Vote on Options | 1 | 2002-01-24 10:11 | 2002-01-24 10:12
32 | Dialog A | 5 | 2002-01-24 10:12 | 2002-01-24 10:17
33 | Vote on Options | 1 | 2002-01-24 10:17 | 2002-01-24 10:18
34 | Dialog B | 5 | 2002-01-24 10:18 | 2002-01-24 10:23
35 | Vote on Options | 1 | 2002-01-24 10:23 | 2002-01-24 10:24
36 | Decision Maker Decides | 5 | 2002-01-24 10:24 | 2002-01-24 10:29
37 | Assign Tasks | 5 | 2002-01-24 10:29 | 2002-01-24 10:34
38 | Work Tasks | 1 Day | 2002-01-24 10:34 | 2002-01-25 10:34
39 | Tollgate Review | 1 | 2002-01-25 10:34 | 2002-01-25 11:34
40 | Analyze | 2 Wks | 2002-01-25 11:34 | 2002-02-08 09:44
41 | FMEA Meeting 1 | 92 | 2002-01-25 11:34 | 2002-01-25 14:06
42 | Review Status | 10 | 2002-01-25 11:34 | 2002-01-25 11:44
43 | Review Schedule | 5 | 2002-01-25 11:44 | 2002-01-25 11:49
44 | FMEA | 72 | 2002-01-25 11:49 | 2002-01-25 14:01
45 | Goal | 2 | 2002-01-25 11:49 | 2002-01-25 11:51
46 | Process | 5 | 2002-01-25 11:51 | 2002-01-25 11:56
47 | Exercise | 1 | 2002-01-25 11:56 | 2002-01-25 13:56
48 | Review | 5 | 2002-01-25 13:56 | 2002-01-25 14:01
49 | Assign Tasks | 5 | 2002-01-25 14:01 | 2002-01-25 14:06
50 | Work Tasks | 4 Days | 2002-01-25 14:01 | 2002-01-31 14:01
51 | FMEA Meeting 2 | 92 | 2002-01-31 14:01 | 2002-01-31 15:33
52 | Review Status | 10 | 2002-01-31 14:01 | 2002-01-31 14:11
53 | Review Schedule | 5 | 2002-01-31 14:11 | 2002-01-31 14:16
54 | FMEA | 72 | 2002-01-31 14:16 | 2002-01-31 15:28
55 | Goal | 2 | 2002-01-31 14:16 | 2002-01-31 14:18
56 | Process | 5 | 2002-01-31 14:18 | 2002-01-31 14:23
57 | Exercise | 1 | 2002-01-31 14:23 | 2002-01-31 15:23
58 | Review | 5 | 2002-01-31 15:23 | 2002-01-31 15:28
59 | Assign Tasks | 5 | 2002-01-31 15:28 | 2002-01-31 15:33
60 | Work Tasks | 4 Days | 2002-01-31 15:33 | 2002-02-06 15:33
61 | FMEA and Data Analysis Meeting | 78 | 2002-02-06 15:33 | 2002-02-06 16:51
62 | Review Status | 10 | 2002-02-06 15:33 | 2002-02-06 15:43
63 | Review Schedule | 5 | 2002-02-06 15:43 | 2002-02-06 15:48
64 | FMEA | 0.5 | 2002-02-06 15:48 | 2002-02-06 16:17
65 | Summary | 2 | 2002-02-06 15:48 | 2002-02-06 15:50
66 | Dialog A | 5 | 2002-02-06 15:50 | 2002-02-06 15:55
67 | Details | 10 | 2002-02-06 15:55 | 2002-02-06 16:07
68 | Dialog B | 5 | 2002-02-06 16:07 | 2002-02-06 16:12
69 | Review | 5 | 2002-02-06 16:12 | 2002-02-06 16:17
70 | Data Analysis Review | 29 | 2002-02-06 16:17 | 2002-02-06 16:46
71 | Summary | 2 | 2002-02-06 16:17 | 2002-02-06 16:19
72 | Dialog A | 5 | 2002-02-06 16:19 | 2002-02-06 16:24
73 | Details | 10 | 2002-02-06 16:24 | 2002-02-06 16:36
74 | Dialog B | 5 | 2002-02-06 16:36 | 2002-02-06 16:41
75 | Review | 5 | 2002-02-06 16:41 | 2002-02-06 16:46
76 | Assign Tasks | 5 | 2002-02-06 16:46 | 2002-02-06 16:51
77 | Work Tasks | 1 Day | 2002-02-06 16:51 | 2002-02-07 16:51
78 | Improvement Direction Meeting | 0.88333 | 2002-02-07 16:51 | 2002-02-08 08:44
79 | Review Status | 10 | 2002-02-07 16:51 | 2002-02-08 08:01
80 | Review Schedule | 5 | 2002-02-08 08:01 | 2002-02-08 08:06
81 | Improvement Direction Decision | 0.5 | 2002-02-08 08:06 | 2002-02-08 08:39
82 | Clarify Options | 10 | 2002-02-08 08:06 | 2002-02-08 08:16
83 | ID Decision Maker | 2 | 2002-02-08 08:16 | 2002-02-08 08:18
84 | Vote on Options | 2 | 2002-02-08 08:18 | 2002-02-08 08:20
85 | Dialog A | 5 | 2002-02-08 08:20 | 2002-02-08 08:25
86 | Vote on Options | 2 | 2002-02-08 08:25 | 2002-02-08 08:27
87 | Dialog B | 5 | 2002-02-08 08:27 | 2002-02-08 08:32
88 | Vote on Options | 2 | 2002-02-08 08:32 | 2002-02-08 08:34
89 | Decision Maker Decides | 5 | 2002-02-08 08:34 | 2002-02-08 08:39
90 | Assign Tasks | 5 | 2002-02-08 08:39 | 2002-02-08 08:44
91 | Tollgate Review | 1 | 2002-02-08 08:44 | 2002-02-08 09:44
92 | Improve | 3 Wks | 2002-02-08 09:44 | 2002-02-28 13:48
93 | Work Tasks | 4 Days | 2002-02-08 09:44 | 2002-02-14 09:44
94 | Process Map Meeting | 72 | 2002-02-14 09:44 | 2002-02-14 10:56
95 | Review Status | 10 | 2002-02-14 09:44 | 2002-02-14 09:54
96 | Report Weekly Deliverable | 10 | 2002-02-14 09:54 | 2002-02-14 10:04
97 | Review Schedule | 5 | 2002-02-14 10:04 | 2002-02-14 10:09
98 | Process Map | 42 | 2002-02-14 10:09 | 2002-02-14 10:51
99 | Goal | 2 | 2002-02-14 10:09 | 2002-02-14 10:11
100 | Process | 5 | 2002-02-14 10:11 | 2002-02-14 10:16
101 | Exercise | 0.5 | 2002-02-14 10:16 | 2002-02-14 10:46
102 | Review | 5 | 2002-02-14 10:46 | 2002-02-14 10:51
103 | Assign Tasks | 5 | 2002-02-14 10:51 | 2002-02-14 10:56
104 | Work Tasks | 1 Wk | 2002-02-14 10:56 | 2002-02-21 10:56
105 | Control Plan Meeting | 1 | 2002-02-21 10:56 | 2002-02-21 11:48
106 | Review Status | 5 | 2002-02-21 10:56 | 2002-02-21 11:01
107 | Report Weekly Deliverable | 10 | 2002-02-21 11:01 | 2002-02-21 11:11
108 | Review Schedule | 5 | 2002-02-21 10:56 | 2002-02-21 11:01
109 | Control Plan Tool Meeting | 42 | 2002-02-21 11:01 | 2002-02-21 11:43
110 | Goal | 2 | 2002-02-21 11:01 | 2002-02-21 11:03
111 | Process | 5 | 2002-02-21 11:03 | 2002-02-21 11:08
112 | Exercise | 0.5 | 2002-02-21 11:08 | 2002-02-21 11:38
113 | Review | 5 | 2002-02-21 11:38 | 2002-02-21 11:43
114 | Assign Tasks | 5 | 2002-02-21 11:43 | 2002-02-21 11:48
115 | Work Tasks | 1 Wk | 2002-02-21 11:48 | 2002-02-28 11:48
116 | Tollgate Review | 1 | 2002-02-28 11:48 | 2002-02-28 13:48
117 | Control | 4 Wks | 2002-02-28 13:48 | 2002-03-28 13:48
118 | Tollgate Review | 1 | 2002-03-28 13:48 | 2002-03-28 14:48

## GC Plan
Gage Control Plan
[12 empty] | Page: | of | of
| Gage Information |  |  |  | Personnel Information | [6 empty] | Document No:
| Gage Name |  |  |  | Department | [6 empty] | Revision Date:
| Gage ID/Serial Number |  |  |  | Storage Location | [6 empty] | Supercedes:
| Gage Type |  |  |  | Responsible Storage | [6 empty] | Frequency:
| Reference Information |  |  |  | Responsible MSA
Calibration Procedure
Handling and Storage
Maintenance
Spare Parts
|  | Date | Resolution | Bias | Linearity | Stability | Calibration |  | GR&R |  |  | Notes
[7 empty] | Date | By | %R&R | P/T | Disc Index
Baseline
In-Service
In-Service
In-Service
In-Service
In-Service
In-Service
In-Service
In-Service

## HOQ
| Relationship Matrix 9=Strong, 3=Moderate, 1=Weak |  | Quality of Service | Staffing Levels | Call Volume | Call Routing | Training | Systems Problems | Information Sources: Speed/Availability | Call Blocking | Availability of Other Depts | Exception Processing | Rework Reduction | Experience Level of Reps | Delivery of Info | Technology Limitations |  | How Important | Baseline | Metric | Target
Management | Service Level
IVR Usage
Call Work
Productivity and Calls Per Hour
Cost
Risk Exposure
Compliance
External Client | POC Resolution
Call Duration and Hold Time
Call Backs
Call Transferred
Call Blocked
Time in Queue
| How Important | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metric
Target

## C&E Matrix
Rating of Importance to Customer
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Process Inputs | [16 empty] | Total
1 | [16 empty] | 0
2 | [16 empty] | 0
3 | [16 empty] | 0
4 | [16 empty] | 0
5 | [16 empty] | 0
6 | [16 empty] | 0
7 | [16 empty] | 0
8 | [16 empty] | 0
9 | [16 empty] | 0
10 | [16 empty] | 0
11 | [16 empty] | 0
12 | [16 empty] | 0
13 | [16 empty] | 0
14 | [16 empty] | 0
15 | [16 empty] | 0
16 | [16 empty] | 0
17 | [16 empty] | 0
18 | [16 empty] | 0
19 | [16 empty] | 0
20 | [16 empty] | 0
0
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cause & Effect Matrix
This table provides the initial input to the FMEA. When each of the output variables (requirements) are not correct, that represents potential "EFFECTS". When each input variable is not correct, that represents "CAUSES".
1. List the Key Process Output Variables
2. Rate each variable on a 1-to-10 scale to importance to the customer
3. List Key Process Input Variables
4. Rate each variables relationship to each output variable on a 1-to-10 scale
5. Select the top input variables to start the FMEA process; Determine how each selected input variable can "go wrong" and place that in the Cause column of the FMEA.

## FMEAInfo
PFMEA Number:
Process Name:
Process Responsibility:
Prepared By:
Affected Product(s):
PFMEA Key Date:
PFMEA Origination Date:
PFMEA Revision Date:
Core Team Members:
Potential Failure Modes and Effects Analysis (Information Sheet)

## FMEA
Process or Product Name: | [6 empty] | Prepared by: |  |  | Page ____ of ____
Responsible: | [6 empty] | FMEA Date (Orig) ______________ (Rev) _____________
Process Step | Key Process Input | Potential Failure Mode | Potential Failure Effects | SEV | Potential Causes | OCC | Current Controls | DET | RPN | Actions Recommended | Resp. | Actions Taken | SEV | OCC | DET | RPN
What is the process step | What is the Key Process Input? | In what ways does the Key Input go wrong? | What is the impact on the Key Output Variables (Customer Requirements) or internal requirements? | How Severe is the effect to the customer? | What causes the Key Input to go wrong? | How often does cause or FM occur? | What are the existing controls and procedures (inspection and test) that prevent either the cause or the Failure Mode? Should include an SOP number. | How well can you detect cause or FM? |  | What are the actions for reducing the occurrence of the Cause, or improving detection? Should have actions only on high RPN's or easy fixes. | Whose Responsible for the recommended action? | What are the completed actions taken with the recalculated RPN? Be sure to include completion month/year
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
Process / Product
Failure Modes and Effects Analysis
(FMEA)

## FSeverity
Effect | Criteria: Severity of Effect Defined | Ranking
Hazardous: Without Warning | May endanger operator. Failure mode affects safe vehicle operation and / or involves noncompliance with government regulation. Failure will occur WITHOUT warning. | 10
Hazardous: With Warning | May endanger operator. Failure mode affects safe vehicle operation and / or involves noncompliance with government regulation. Failure will occur WITH warning. | 9
Very High | Major disruption to production line. 100% of product may have to be scrapped. Vehicle / item inoperable, loss of primary function. Customer very dissatisfied. | 8
High | Minor disruption to production line. Product may have to be sorted and a portion (less than 100%) scrapped. Vehicle operable, but at a reduced level of performance. Customer dissatisfied. | 7
Moderate | Minor disruption to production line. A portion (less than 100%) may have to be scrapped (no sorting). Vehicle / item operable, but some comfort / convenience item(s) inoperable. Customers experience discomfort. | 6
Low | Minor disruption to production line. 100% of product may have to be reworked. Vehicle / item operable, but some comfort / convenience item(s) operable at reduced level of performance. Customer experiences some dissatisfaction. | 5
Very Low | Minor disruption to production line. The product may have to be sorted and a portion (less than 100%) reworked. Fit / finish / squeak / rattle item does not conform. Defect noticed by most customers. | 4
Minor | Minor disruption to production line. A portion (less than 100%) of the product may have to be reworked on-line but out-of-station. Fit / finish / squeak / rattle item does not conform. Defect noticed by average customers. | 3
Very Minor | Minor disruption to production line. A portion (less than 100%) of the product may have to be reworked on-line but in-station. Fit / finish / squeak / rattle item does not conform. Defect noticed by discriminating customers. | 2
None | No effect. | 1

## FOccurance
Probability of Failure | Possible Failure Rates | Cpk | Ranking
Very High: | ³ 1 in 2 | < 0.33 | 10
Failure is almost inevitable | 1 in 3 | ³ 0.33 | 9
High: Generally associated with processes similar to previous | 1 in 8 | ³ 0.51 | 8
processes that have often failed | 1 in 20 | ³ 0.67 | 7
Moderate: Generally associated with processes similar to | 1 in 80 | ³ 0.83 | 6
previous processes which have | 1 in 400 | ³ 1.00 | 5
experienced occasional failures, but not in major proportions | 1 in 2,000 | ³ 1.17 | 4
Low: Isolated failures associated with similar processes | 1 in 15,000 | ³ 1.33 | 3
Very Low: Only isolated failures associated with almost identical processes | 1 in 150,000 | ³ 1.5 | 2
Remote: Failure is unlikely. No failures ever associated with almost identical processes | £ 1 in 1,500,000 | ³ 1.67 | 1

## FDetection
Detection | Criteria: Likelihood the existence of a defect will be detected by test content before product advances to next or subsequent process | Ranking
Almost Impossible | Test content detects < 80 % of failures | 10
Very Remote | Test content must detect 80 % of failures | 9
Remote | Test content must detect 82.5 % of failures | 8
Very Low | Test content must detect 85 % of failures | 7
Low | Test content must detect 87.5 % of failures | 6
Moderate | Test content must detect 90 % of failures | 5
Moderately High | Test content must detect 92.5 % of failures | 4
High | Test content must detect 95 % of failures | 3
Very High | Test content must detect 97.5 % of failures | 2
Almost Certain | Test content must detect 99.5 % of failures | 1

## ControlPlan
| Core Team: | [6 empty] | Date (Orig):
Date (Rev):
Process Step | Input | Output | Process Spec (LSL, USL, Target) | Cpk / Date (Sample Size) | Measurement System | %R&R or P/T | Current Control Method (from FMEA) | Who | Where | When | Reaction Plan
Control Plan
Current Control Plan

## Process Control Plan
Six Sigma Process Control Plan
| Process Name: | [6 empty] | Prepared by: | [5 empty] | Page: |  | of
| Customer |  |  |  |  | Int/Ext |  | Approved by: | [5 empty] | Document No:
| Location: | [6 empty] | Approved by: | [5 empty] | Revision Date:
| Area: | [6 empty] | Approved by: | [5 empty] | Supercedes:
Sub Process |  | Sub Process Step | CTQ |  | Specification Characteristic | Specification/ Requirement | Measurement Method |  | Sample Size | Frequency | Who Measures | Where Recorded | Decision Rule/ Corrective Action |  | SOP Reference
|  |  | KPOV | KPIV |  | USL LSL

## SS Prvnt Mnt
Six Sigma Preventative Maintenance Plan
| Process Name: | [6 empty] | Prepared by: | [5 empty] | Page: |  | of
| Customer |  |  |  |  | Int/Ext |  | Approved by: | [5 empty] | Document No:
| Location: | [6 empty] | Approved by: | [5 empty] | Revision Date:
| Area: | [6 empty] | Approved by: | [5 empty] | Supercedes:
System |  | Failure Mode | CTQ |  | Predictor | Predictor Level | Measurement Method |  | Sample Size | Frequency | Who Measures | Where Recorded | Decision Rule/ Corrective Action |  | SOP Reference
|  |  | KPOV | KPIV |  | USL LSL

## Outputs
Customer Requirement (Output Variable) | Measurement Technique | %R&R or P/T Ratio | Upper Spec Limit | Target | Lower Spec Limit | Cp | Cpk | Sample Size | Date | Actions
Key Process Output Variable
Capability Status Sheet

## DFMEA Template
Failure Mode and Effects Analysis
[7 empty] | (Design FMEA) |  |  |  | FMEA Number:
[11 empty] | Page |  | of
System/Component: |  |  |  | Design Responsibility: | [6 empty] | Prepared by:
[11 empty] | FMEA Date (Orig.) |  | (Rev.)
Core Team:
Item / Process Function | Potential Failure Mode | Potential Effect(s) of Failure | S e v | Potential Cause(s)/ Mechanism(s) of Failure | O c c u r | Current Design Controls Prevention | Current Design Controls Detection | D e t e c | R. P. N. | Recommended Action(s) | Responsibility & Target Completion Date | Action Results
[12 empty] | ActionsTaken | S e v | O c c u r | D e t e c | R. P. N.
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0

## Z-Table
The value in the table is the right tail probability.
Hundredth place for Z-value
Z-Value | 0 | 0.01 | 0.02 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09
0 | 0.5 | 0.49601 | 0.49202 | 0.48803 | 0.48405 | 0.48006 | 0.47608 | 0.4721 | 0.46812 | 0.46414
0.1 | 0.46017 | 0.4562 | 0.45224 | 0.44828 | 0.44433 | 0.44038 | 0.43644 | 0.43251 | 0.42858 | 0.42465
0.2 | 0.42074 | 0.41683 | 0.41294 | 0.40905 | 0.40517 | 0.40129 | 0.39743 | 0.39358 | 0.38974 | 0.38591
0.3 | 0.38209 | 0.37828 | 0.37448 | 0.3707 | 0.36693 | 0.36317 | 0.35942 | 0.35569 | 0.35197 | 0.34827
0.4 | 0.34458 | 0.3409 | 0.33724 | 0.3336 | 0.32997 | 0.32636 | 0.32276 | 0.31918 | 0.31561 | 0.31207
0.5 | 0.30854 | 0.30503 | 0.30153 | 0.29806 | 0.2946 | 0.29116 | 0.28774 | 0.28434 | 0.28096 | 0.2776
0.6 | 0.27425 | 0.27093 | 0.26763 | 0.26435 | 0.26109 | 0.25785 | 0.25463 | 0.25143 | 0.24825 | 0.2451
0.7 | 0.24196 | 0.23885 | 0.23576 | 0.2327 | 0.22965 | 0.22663 | 0.22363 | 0.22065 | 0.2177 | 0.21476
0.8 | 0.21186 | 0.20897 | 0.20611 | 0.20327 | 0.20045 | 0.19766 | 0.19489 | 0.19215 | 0.18943 | 0.18673
0.9 | 0.18406 | 0.18141 | 0.17879 | 0.17619 | 0.17361 | 0.17106 | 0.16853 | 0.16602 | 0.16354 | 0.16109
1 | 0.15866 | 0.15625 | 0.15386 | 0.15151 | 0.14917 | 0.14686 | 0.14457 | 0.14231 | 0.14007 | 0.13786
1.1 | 0.13567 | 0.1335 | 0.13136 | 0.12924 | 0.12714 | 0.12507 | 0.12302 | 0.121 | 0.119 | 0.11702
1.2 | 0.11507 | 0.11314 | 0.11123 | 0.10935 | 0.10749 | 0.10565 | 0.10383 | 0.10204 | 0.10027 | 0.098525
1.3 | 0.0968 | 0.095098 | 0.093418 | 0.091759 | 0.090123 | 0.088508 | 0.086915 | 0.085343 | 0.083793 | 0.082264
1.4 | 0.080757 | 0.07927 | 0.077804 | 0.076359 | 0.074934 | 0.073529 | 0.072145 | 0.070781 | 0.069437 | 0.068112
1.5 | 0.066807 | 0.065522 | 0.064255 | 0.063008 | 0.06178 | 0.060571 | 0.05938 | 0.058208 | 0.057053 | 0.055917
1.6 | 0.054799 | 0.053699 | 0.052616 | 0.051551 | 0.050503 | 0.049471 | 0.048457 | 0.04746 | 0.046479 | 0.045514
1.7 | 0.044565 | 0.043633 | 0.042716 | 0.041815 | 0.04093 | 0.040059 | 0.039204 | 0.038364 | 0.037538 | 0.036727
1.8 | 0.03593 | 0.035148 | 0.03438 | 0.033625 | 0.032884 | 0.032157 | 0.031443 | 0.030742 | 0.030054 | 0.029379
1.9 | 0.028717 | 0.028067 | 0.027429 | 0.026803 | 0.02619 | 0.025588 | 0.024998 | 0.024419 | 0.023852 | 0.023295
2 | 0.02275 | 0.022216 | 0.021692 | 0.021178 | 0.020675 | 0.020182 | 0.019699 | 0.019226 | 0.018763 | 0.018309
2.1 | 0.017864 | 0.017429 | 0.017003 | 0.016586 | 0.016177 | 0.015778 | 0.015386 | 0.015003 | 0.014629 | 0.014262
2.2 | 0.013903 | 0.013553 | 0.013209 | 0.012874 | 0.012545 | 0.012224 | 0.011911 | 0.011604 | 0.011304 | 0.011011
2.3 | 0.010724 | 0.010444 | 0.01017 | 0.0099031 | 0.0096419 | 0.0093867 | 0.0091375 | 0.008894 | 0.0086563 | 0.0084242
2.4 | 0.0081975 | 0.0079763 | 0.0077603 | 0.0075494 | 0.0073436 | 0.0071428 | 0.0069469 | 0.0067557 | 0.0065691 | 0.0063872
2.5 | 0.0062097 | 0.0060366 | 0.0058677 | 0.0057031 | 0.0055426 | 0.0053861 | 0.0052336 | 0.0050849 | 0.00494 | 0.0047988
2.6 | 0.0046612 | 0.0045271 | 0.0043965 | 0.0042692 | 0.0041453 | 0.0040246 | 0.003907 | 0.0037926 | 0.0036811 | 0.0035726
2.7 | 0.003467 | 0.0033642 | 0.0032641 | 0.0031667 | 0.003072 | 0.0029798 | 0.0028901 | 0.0028028 | 0.0027179 | 0.0026354
2.8 | 0.0025551 | 0.0024771 | 0.0024012 | 0.0023274 | 0.0022557 | 0.002186 | 0.0021182 | 0.0020524 | 0.0019884 | 0.0019262
2.9 | 0.0018658 | 0.0018071 | 0.0017502 | 0.0016948 | 0.0016411 | 0.0015889 | 0.0015382 | 0.001489 | 0.0014412 | 0.0013949
3 | 0.0013499 | 0.0013062 | 0.0012639 | 0.0012228 | 0.0011829 | 0.0011442 | 0.0011067 | 0.0010703 | 0.001035 | 0.0010008
3.1 | 0.0009676 | 0.00093544 | 0.00090426 | 0.00087403 | 0.00084474 | 0.00081635 | 0.00078885 | 0.00076219 | 0.00073638 | 0.00071136
3.2 | 0.00068714 | 0.00066367 | 0.00064095 | 0.00061895 | 0.00059765 | 0.00057703 | 0.00055706 | 0.00053774 | 0.00051904 | 0.00050094
3.3 | 0.00048342 | 0.00046648 | 0.00045009 | 0.00043423 | 0.00041889 | 0.00040406 | 0.00038971 | 0.00037584 | 0.00036243 | 0.00034946
3.4 | 0.00033693 | 0.00032481 | 0.00031311 | 0.00030179 | 0.00029086 | 0.00028029 | 0.00027009 | 0.00026023 | 0.00025071 | 0.00024151
3.5 | 0.00023263 | 0.00022405 | 0.00021577 | 0.00020778 | 0.00020006 | 0.00019262 | 0.00018543 | 0.00017849 | 0.0001718 | 0.00016534
3.6 | 0.00015911 | 0.0001531 | 0.0001473 | 0.00014171 | 0.00013632 | 0.00013112 | 0.00012611 | 0.00012128 | 0.00011662 | 0.00011213
3.7 | 0.0001078 | 0.00010363 | 9.9611e-05 | 9.574e-05 | 9.201e-05 | 8.8417e-05 | 8.4957e-05 | 8.1624e-05 | 7.8414e-05 | 7.5324e-05
3.8 | 7.2348e-05 | 6.9483e-05 | 6.6726e-05 | 6.4072e-05 | 6.1517e-05 | 5.9059e-05 | 5.6694e-05 | 5.4418e-05 | 5.2228e-05 | 5.0122e-05
3.9 | 4.8096e-05 | 4.6148e-05 | 4.4274e-05 | 4.2473e-05 | 4.0741e-05 | 3.9076e-05 | 3.7475e-05 | 3.5936e-05 | 3.4458e-05 | 3.3037e-05
4 | 3.1671e-05 | 3.0359e-05 | 2.9099e-05 | 2.7888e-05 | 2.6726e-05 | 2.5609e-05 | 2.4536e-05 | 2.3507e-05 | 2.2518e-05 | 2.1569e-05
Z